## Sheet1
# | MILESTONE | COST ESTIMATE | ACTUAL COST | TIME ESTIMATE (hours) | STATUS
1 | Monero Bisq Wallet: view balance, send, receive, list, search and verify transactions | 8700 | 6750 | 224 | DELIVERED
2 | Switch to monero-java-lite and implement 2/2 multisig support in wallet | 300 |  | 16 | ON HOLD
3 | Mirror current trade interface with Monero as base currency partitioning from BTC-based trades | 6500 |  | 160 | DELIVERED
4 | Implement Monero trade (buy) services linking to wallet through monero-java-lite | 13500 |  | 354 | PENDING
4.a | Create trade (modify & extend existing component) | 3500 |  | 120 | DELIVERED
4.b | Stage 1: Wait for blockchain confirmation (use 2/2 multisig wallet to initiate trade) | 5000 |  | 130 | PENDING
4.c | Stage 2: Start payment (modify & extend existing component) | 1500 |  | 40 | PENDING
4.d | Stage 3: Wait until payment arrived (modify & extend existing component) | 1500 |  | 40 | PENDING
4.e | Stage 4: Completed (again use 2/2 multisig wallet to finalize trade) | 2000 |  | 24 | PENDING
5 | Implement Monero trade (sell) services using 3 & 4 above as templates | 2000 |  | 40 | PENDING